## _Lists
Dropdown Lists - do not edit unless updating allowed values | [11 empty] | CandidateCategory
Shortlisted
Status | Risk | Phase | Tool | YesNo | ActionType | SourceType | FileType | ResourceType | Stage | Severity | Milestone_Status | Under Shortlisting
Not Started | Low | Pilot | Laser AI | Yes | Decision | Email | RIS | Folder | Review selection and onboarding | Low | Complete | Future Phase
Pending | Medium | Phase 1 | Nested Knowledge | No | ToDo | Meeting | PDFs | Protocol | Setup package and data item readiness | Medium | Active | Not Eligible
Under Review | High | Phase 2 | Tool A |  | MoMAction | MoM | Criteria | Presentation | Abstract screening | High | Risk | On Hold
In Progress | TBD | Governance | Tool B |  | FollowUp | Call | Extraction | Survey | Full-text readiness and screening |  | Pending | Clarification Needed
Waiting on Others |  | MoM | Allocated tool pending |  | Escalation | Document | Protocol | Template | Data extraction |  | Blank | Withdrawn
Needs Action |  |  | AI tool pending |  | CrossPhase | Dashboard | Time Log | Excel | Analysis and downstream work
Blocked |  |  | TBD |  |  | Other |  | Spreadsheet
Complete | [7 empty] | PDF
Complete / Under Review | [7 empty] | MeetingNotes
Ready | [7 empty] | Link
Missing
Scheduled
Sent
Active
Open
Closed
Not Applicable
Not Eligible
Not Yet Required
Wrapping Up
Starts 20 May
TBD
To Be Updated
On Track
Withdrawn

## Update_Guide
Cochrane AI Platform Study Dashboard Backend
Purpose | This workbook is structured for dashboard content only. Do not store full project archives or long background notes here.
Main rule | Each review has one sheet. Within each review sheet, sections are stacked vertically. Nothing is placed side-by-side, so rows can be added/deleted with lower risk.
Dashboard screens | Executive Review Card; Review Detail; Operations / Visual Tracker; Files; Communication Log; Critical Items; Resources; Upcoming Meetings.
63 actions | The full 63-step workflow is included in Workflow_63_Actions and repeated in each review sheet under the Review Workflow Status section.
How to update | Update only cells in the Value, Status, Owner, DueDate, Notes, and Display columns. Add rows inside the relevant section table when needed.
Avoid | Do not add sections to the right of existing content. Add new sections below the current sections.
Exporter note | The dashboard exporter should read by section/table names rather than fixed cell coordinates.
Latest change | Updated 2026-07-30: Fruit & Vegetable AI abstract screening complete; conventional consolidation and full-text setup pending.
Dropdowns | Dropdown validations added for Status, Risk, Phase, Tool, Yes/No, SourceType, FileType, ResourceType, Stage, Severity, and Milestone_Status.
Review sheets | Sections remain stacked vertically. You can add/delete rows within sections, but keep the section headers and column names stable.
Workflow_Master | Kept as a separate sheet matching the old Excel backend. Workflow_63_Actions mirrors the same content for readability.
Do not store | Avoid adding internal archive notes that will not display in the dashboard.
New_Reviews sheet | Use for continuous onboarding pipeline before a review becomes a full dashboard review sheet. Keep entries brief: review name, category/status, target phase, owner/contact, and remarks.

## Review_Index
ReviewID | ShortName | ReviewTitle | Phase | Status | Risk | Tool | Lead | CurrentStage | NextAction | TargetDate | Assessment | DisplayInHTML | ReviewSheet
pilot-01 | Caffeine | Cessation of caffeine | Pilot | Closed | Medium | TBD | Matteo Bruschettini | Pilot closeout closed |  | 2026-05-10 | Closed | Yes | pilot-01 Caffeine
pilot-02 | DMARDs / RA | DMARDs / Rheumatoid arthritis | Pilot | Closed | Medium | TBD | Jordi Pardo Pardo / Glen Hazlewood | Pilot closeout closed |  | 2026-05-13 | Closed | Yes | pilot-02 DMARDs RA
phase1-01 | BP Targets | Blood pressure targets for hypertension in people with diabetes mellitus | Phase 1 | Full-text screening | Low | Laser AI | Doreen Larvie | Full-text screening nearing completion; data extraction setup underway | Complete full-text screening by 2026-07-08 and continue data extraction setup | 2026-07-08 | In Progress | Yes | phase1-01 BP Targets
phase1-02 | Psoriasis | Systemic pharmacological treatments for chronic plaque psoriasis | Phase 1 | Abstract Screening | Low | Nested Knowledge | Laurence Le Cleach / Sivem Afach | Conventional title/abstract screening nearing completion; AI-assisted full-text selection almost complete; data extraction preparation/sample planning underway | Complete conventional title/abstract screening; prepare common sample of up to 10 studies for later data extraction | TBD | In Progress | Yes | phase1-02 Psoriasis
phase1-03 | Fruit & Veg | Interventions for increasing fruit and vegetable consumption in children aged five years and under | Phase 1 | AI-assisted abstract screening complete | Medium | Laser AI | Rebecca K. Hodder | Laser AI abstract screening is complete. Fifteen studies have advanced to full-text screening. The conventional team is consolidating its abstract-screening results. | Complete the usability survey, await conventional-team consolidation, retrieve the PDFs for the 15 studies, and proceed with full-text screening setup. | TBD | In Progress | Yes | phase1-03 Fruit & Veg
phase1-04 | Med Adherence | Interventions for improving medication-taking ability and adherence in older adults prescribed multiple medications | Phase 1 | Withdrawn | Low | Nested Knowledge | Amanda Cross / Rehan Sarwar | Team has withdrawn from the platform study due to capacity constraints | Retain as withdrawn/historical record; no active follow-up required |  | Withdrawn | No | phase1-04 Med Adherence
phase1-05 | Vitamin C | Vitamin C supplementation for prevention and treatment of pneumonia | Phase 1 | Setup phase | Medium | Laser AI | Syeda Kanza Naqvi / Jai Das | Setup phase underway; Laser AI allocated; search/LILACS clarification and remaining setup materials are being finalized; abstract screening has not yet commenced | Complete setup materials and Laser AI configuration before commencing abstract screening | TBD | In Progress | Yes | phase1-05 Vitamin C
phase2-01 | Phase 2 Batch | Phase 2 Batch | Phase 2 | Scheduled | Medium | TBD | TBD | Future batch planning | Keep placeholders until Phase 1 stabilizes. | TBD | Not Started | Yes | phase2-01 Phase 2 Batch
phase1-06 | Probiotics AAD | Probiotics for the prevention of paediatric antibiotic-associated diarrhoea | Phase 1 | Onboarded / awaiting template revisions | Medium | Nested Knowledge | Jeremy Steen / Bradley Johnston | Onboarding and tool training completed; RIS file, protocol, eligibility criteria, and draft data extraction template received | Await final template revisions before project configuration and screening begin | TBD | In Progress | Yes | phase1-06 Probiotics
phase1-07 | Human Milk Fortifier | Human milk-derived versus bovine milk-derived fortifier for prevention of mortality and morbidity in preterm neonates | Phase 1 | Onboarding / materials collection | Medium | Nested Knowledge | Mohan Pammi | Participation confirmed; team roles agreed; onboarding and study material collection underway; tool training pending | Collect study materials, complete Nested Knowledge tool training, and configure project for screening | TBD | In Progress | Yes | phase1-07 Human Milk

## Workflow_63_Actions
Workflow Master | Column1 | Column2 | Column3 | Column4 | Column5 | Column6
Use row 4 onward for data entry. Keep IDs stable for GitHub/data.js export.
WorkflowStepID | StepOrder | WorkflowGroup | ShortName | FullActivity | ResponsibleDefault | DependsOn | Blocks | DefaultStatus | DisplayInHTML | DisplayOrder | InternalNotes
w01 | 1 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Not Started | Yes | 1
w02 | 2 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Not Started | Yes | 2
w03 | 3 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Not Started | Yes | 3
w04 | 4 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Not Started | Yes | 4
w05 | 5 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Not Started | Yes | 5
w06 | 6 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Not Started | Yes | 6
w07 | 7 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Not Started | Yes | 7
w08 | 8 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Not Started | Yes | 8
w09 | 9 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started | Yes | 9
w10 | 10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Not Started | Yes | 10
w11 | 11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Not Started | Yes | 11
w12 | 12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Not Started | Yes | 12
w13 | 13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Not Started | Yes | 13
w14 | 14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Not Started | Yes | 14
w15 | 15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Not Started | Yes | 15
w16 | 16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Not Started | Yes | 16
w17 | 17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started | Yes | 17
w18 | 18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started | Yes | 18
w19 | 19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started | Yes | 19
w20 | 20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started | Yes | 20
w21 | 21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started | Yes | 21
w22 | 22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started | Yes | 22
w23 | 23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started | Yes | 23
w24 | 24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started | Yes | 24
w25 | 25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started | Yes | 25
w26 | 26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started | Yes | 26
w27 | 27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started | Yes | 27
w28 | 28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started | Yes | 28
w29 | 29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started | Yes | 29
w30 | 30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started | Yes | 30
w31 | 31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started | Yes | 31
w32 | 32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started | Yes | 32
w33 | 33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started | Yes | 33
w34 | 34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started | Yes | 34
w35 | 35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started | Yes | 35
w36 | 36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started | Yes | 36
w37 | 37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started | Yes | 37
w38 | 38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started | Yes | 38
w39 | 39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started | Yes | 39
w40 | 40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started | Yes | 40
w41 | 41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started | Yes | 41
w42 | 42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started | Yes | 42
w43 | 43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started | Yes | 43
w44 | 44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started | Yes | 44
w45 | 45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started | Yes | 45
w46 | 46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started | Yes | 46
w47 | 47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started | Yes | 47
w48 | 48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started | Yes | 48
w49 | 49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started | Yes | 49
w50 | 50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started | Yes | 50
w51 | 51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started | Yes | 51
w52 | 52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started | Yes | 52
w53 | 53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started | Yes | 53
w54 | 54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started | Yes | 54
w55 | 55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started | Yes | 55
w56 | 56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started | Yes | 56
w57 | 57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started | Yes | 57
w58 | 58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started | Yes | 58
w59 | 59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started | Yes | 59
w60 | 60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started | Yes | 60
w61 | 61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started | Yes | 61
w62 | 62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started | Yes | 62
w63 | 63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started | Yes | 63

## Global_Dashboard
Global Dashboard Content
Phase Strip / Timeline Cards
PhaseKey | PhaseLabel | Window | Note | Display
pilot | Pilot | Mid March to Mid April | Closed | Yes
phase1 | Phase 1 | Mid April to End June | Current Focus | Yes
governance | Interim Analysis | End June | Decision Gate | Yes
phase2 | Phase 2 | Start July to End September | Scheduled | Yes
governance | Report | October | Planned | Yes
Resources Displayed in Dashboard
ResourceID | Name | Type | Owner | Status | URL | Notes | Display
res-001 |  | Folder | Krishna / Core Team | Active |  |  | Yes
res-002 |  | Protocol | Core Team | Active |  |  | Yes
res-003 |  | Presentation | Krishna / Core Team | Active |  |  | Yes
res-006 |  | Spreadsheet | Sean / Krishna | Active |  |  | Yes
res-007 |  | Folder | Andreea / Krishna | To Be Updated |  |  | Yes
Upcoming Meetings Displayed in Dashboard
MeetingID | Date | Title | People | Purpose | Status | Notes | Display
meet-001 | 15 May 2026 | Usability survey tracking discussion |  |  | Completed / No longer required | AI abstract screening completed; conventional consolidation and full-text setup are the next steps. | No
meet-002 | 18 May 2026 | Core team discussion with Meghan |  |  | Sent |  | Yes
meet-003 | 19 May 2026 | BP Targets review team check-in |  |  | Sent |  | Yes
meet-004 | 19 May 2026 | Psoriasis review team check-in |  |  | Sent |  | Yes
meet-005 | 19 May 2026 | Adjudication pilot deadline |  |  | Pending |  | Yes
meet-006 | 21 May 2026 | PM + PI meeting |  |  | Sent |  | Yes

## pilot-01 Caffeine
pilot-01 Caffeine ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | pilot-01 | Yes
ShortName | Caffeine | Yes
ReviewTitle | Cessation of caffeine | Yes
Phase | Pilot | Yes
Status | Closed | Yes
Risk | Medium | Yes
Tool | TBD | Yes
Lead | Matteo Bruschettini | Yes
CurrentStage | Pilot closeout closed | Yes
CurrentUpdate | Pilot closeout record closed; no active follow-up required. | Yes
NextAction |  | No
TargetDate | 2026-05-10 | Yes
Variance | Closed. | Yes
Assessment | Closed | Yes
DisplayInHTML | Yes | Yes | Set to No if review should not appear in dashboard.
LastUpdated | 2026-07-07 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding |  |  |  |  | Yes
setup |  |  |  |  | Yes
abstract |  |  |  |  | Yes
fullText |  |  |  |  | Yes
extraction |  |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | No | Not Started |  |  |  | Yes
PDFs | No | Not Started |  |  |  | Yes
Criteria | No | Not Started |  |  |  | Yes
Extraction | No | Not Started |  |  |  | Yes
Protocol | No | Not Started |  |  |  | Yes
Time Log | No | Not Started |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination | 0 | 0 | Not Started |  |  |  | Yes
Abstract Screening | 0 | 0 | Not Started |  |  |  | Yes
Full-text Screening | 0 | 0 | Not Started |  |  |  | Yes
Data Extraction / Analysis | 0 | 0 | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Not Started |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Not Started |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Not Started |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Not Started |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Not Started |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Not Started |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Not Started |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Not Started |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Not Started |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Not Started |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Not Started |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Not Started |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Not Started |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Not Started |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-pilot-01-001 | Verify Matteo time-on-task values | Krishna / Amin | Complete | Medium | 2026-05-10 | Matteo self-reported time | Closed; no active follow-up required. | Email | 2026-05-07 | No |  | Removed from active dashboard
task-pilot-01-002 | Consolidate usability survey receipt | Susan | Complete | Medium | 2026-05-10 | Survey access | Closed; no active follow-up required. | Email | 2026-05-07 | Yes
task-pilot-01-003 | Capture lessons learned before pilot closeout | Krishna / Core Team | Complete | Medium | 2026-05-10 | Lessons document | Closed; no active follow-up required. | MoM | 2026-05-10 | Yes
Recent Mail / Communication Log Displayed in Dashboard
CommunicationID | Date | Subject | People | Responsible | DueDate | Status | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
comm-pilot-01-001 | 2026-05-07 | Pilot time-on-task update | Matteo Bruschettini | Krishna / Amin | 2026-05-10 | Closed | Closed; no active follow-up required. | task-pilot-01-001 | Verify Matteo time-on-task values | Email |  | No
comm-pilot-01-002 | 2026-05-07 | Pilot survey completion update | Matteo Bruschettini | Krishna / Susan | 2026-05-10 | Closed | Closed; no active follow-up required. | task-pilot-01-002 | Consolidate usability survey receipt | Email |  | Yes
Critical Items Displayed in Dashboard
CriticalItem | Severity | Owner | DueDate | Status | Notes | Display
Full-text time not reported | Medium |  |  | Closed | Closed; no active follow-up required. | No

## pilot-02 DMARDs RA
pilot-02 DMARDs RA ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | pilot-02 | Yes
ShortName | DMARDs / RA | Yes
ReviewTitle | DMARDs / Rheumatoid arthritis | Yes
Phase | Pilot | Yes
Status | Closed | Yes
Risk | Medium | Yes
Tool | TBD | Yes
Lead | Jordi Pardo Pardo / Glen Hazlewood | Yes
CurrentStage | Pilot closeout closed | Yes
CurrentUpdate | Pilot closeout record closed; no active follow-up required. | Yes
NextAction |  | No
TargetDate | 2026-05-13 | Yes
Variance | Closed. | Yes
Assessment | Closed | Yes
DisplayInHTML | Yes | Yes | Set to No if review should not appear in dashboard.
LastUpdated | 2026-07-07 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding |  |  |  |  | Yes
setup |  |  |  |  | Yes
abstract |  |  |  |  | Yes
fullText |  |  |  |  | Yes
extraction |  |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | No | Not Started |  |  |  | Yes
PDFs | No | Not Started |  |  |  | Yes
Criteria | No | Not Started |  |  |  | Yes
Extraction | No | Not Started |  |  |  | Yes
Protocol | No | Not Started |  |  |  | Yes
Time Log | No | Not Started |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination | 0 | 0 | Not Started |  |  |  | Yes
Abstract Screening | 0 | 0 | Not Started |  |  |  | Yes
Full-text Screening | 0 | 0 | Not Started |  |  |  | Yes
Data Extraction / Analysis | 0 | 0 | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Not Started |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Not Started |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Not Started |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Not Started |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Not Started |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Not Started |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Not Started |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Not Started |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Not Started |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Not Started |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Not Started |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Not Started |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Not Started |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Not Started |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-pilot-02-001 | Confirm latest Laser AI progress and outputs | Sean / Laser AI / Review Team | Complete | Medium | 2026-05-13 | Vendor/team update | Closed; no active follow-up required. | MoM | 2026-05-10 | Yes
task-pilot-02-002 | Confirm whether outputs can move toward adjudication preparation | Sean / Laser AI / Review Team | Complete | Medium | 2026-05-13 | Pilot completion status | Closed; no active follow-up required. | MoM | 2026-05-10 | Yes
Recent Mail / Communication Log Displayed in Dashboard
CommunicationID | Date | Subject | People | Responsible | DueDate | Status | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
comm-pilot-02-001 | 2026-05-10 | DMARDs pilot completion follow-up | Core Team / Sean | Sean / Laser AI / Review Team | 2026-05-13 | Closed | Closed; no active follow-up required. | task-pilot-02-001 | Confirm latest Laser AI progress and outputs | MoM |  | Yes
Critical Items Displayed in Dashboard
CriticalItem | Severity | Owner | DueDate | Status | Notes | Display
Pilot output status unclear | Medium |  |  | Closed | Closed; no active follow-up required. | No

## phase1-01 BP Targets
phase1-01 BP Targets ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | phase1-01 | Yes
ShortName | BP Targets | Yes
ReviewTitle | Blood pressure targets for hypertension in people with diabetes mellitus | Yes
Phase | Phase 1 | Yes
Status | Full-text screening | Yes
Risk | Low | Yes
Tool | Laser AI | Yes
Lead | Doreen Larvie | Yes
CurrentStage | Full-text screening nearing completion; data extraction setup underway | Yes
CurrentUpdate | Full-text screening nearing completion; expected completion 2026-07-08; data extraction setup underway | Yes
NextAction | Complete full-text screening by 2026-07-08 and continue data extraction setup | Yes
TargetDate | 2026-07-08 | Yes
Variance | On track for full-text completion; data extraction setup next dependency | Yes
Assessment | In Progress | Yes
DisplayInHTML | Yes | Yes | Set to No if review should not appear in dashboard.
LastUpdated | 2026-07-06 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding | Complete |  |  |  | Yes
setup | Complete |  |  |  | Yes
abstract | Complete |  |  |  | Yes
fullText | Active |  |  |  | Yes
extraction | Setup underway |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | Yes | Ready |  |  |  | Yes
PDFs | No | Not Started |  |  |  | Yes
Criteria | Yes | Ready |  |  |  | Yes
Extraction | Yes | Ready |  |  |  | Yes
Protocol | Yes | Ready |  |  |  | Yes
Time Log | No | Not Started |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination | 0 | 0 | Not Started |  |  |  | Yes
Abstract Screening | 0 | 0 | Not Started |  |  |  | Yes
Full-text Screening | 0 | 0 | Not Started |  |  |  | Yes
Data Extraction / Analysis | 0 | 0 | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Complete |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Complete |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Complete |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Complete |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Complete |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Complete |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Complete |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Complete |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Complete |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Complete |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Complete |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Complete |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Complete |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Complete |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Complete |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Complete |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | In Progress |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Complete |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Complete |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Complete |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Complete |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-phase1-01-001 | Complete Laser AI setup readiness | Response Team / Laser AI | In Progress | Medium | 2026-05-15 | Final data items and review materials | Proceed with Laser AI setup using the final data items file uploaded by Sean. | Email | 2026-05-14 | No
task-phase1-01-002 | Confirm use of final data items file | Sean / Meghan / Response Team | Complete | Low | 2026-05-15 | Final data items file | Sean uploaded the final data items file and Doreen confirmed the final change makes sense. | Email | 2026-05-14 | No
task-phase1-01-003 | Confirm Clockify or alternate time-tracking setup | Krishna | Complete | Medium | Immediate | Reviewer time capture | Offer Clockify or a simple manual stopwatch/Excel method if easier for the review team. | MoM | 2026-05-10 | No
task-phase1-01-004 | Validate abstract screening setup before screening starts | Review Team / Response Team | Pending | Medium | After setup | Setup completion | Do not mark abstract screening active until the setup is validated and reviewers begin screening. | Project tracking | 2026-05-14 | No
task-phase1-01-005 | Confirm AI abstract screening completion | Review Team / Response Team | Complete | Low | 2026-05-27 | AI screening completion | Survey shared after AI screening completion | Email | 2026-05-27 | Yes
task-phase1-01-006 | Collect AI abstract screening usability survey | Review Team | In Progress | Medium | 2026-05-31 | AI abstract screening completion | Survey shared with review team | Email | 2026-05-27 | Yes
task-phase1-01-007 | Confirm human abstract screening status | Doreen Larvie / Review Team | Pending | High | Immediate | Parallel workflow tracking | Asked team to confirm human screening status and time log | Email | 2026-05-27 | Yes
task-phase1-01-008 | Confirm abstract screening time log | Doreen Larvie / Review Team | Pending | Medium | Immediate | Human screening status confirmation | Time recording needed for study analysis | Email | 2026-05-27 | Yes
Recent Mail / Communication Log Displayed in Dashboard
CommunicationID | Date | Subject | People | Responsible | DueDate | Status | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
comm-phase1-01-001 | 2026-05-14 | BP Targets data items finalization | Sean Gardner | Sean / Meghan / Response Team | 2026-05-15 | Complete / Under Review | Sean uploaded the final data items file after moving the instruction “Record timepoint, if applicable” into the instruction field for outcome data items. | task-phase1-01-002 | Confirm use of final data items file | Email |  | No
comm-phase1-01-002 | 2026-05-14 | BP Targets confirmation | Doreen Larvie | Krishna / Response Team | 2026-05-15 | Complete | Doreen confirmed that Sean’s final minor change makes sense. | task-phase1-01-002 | Confirm use of final data items file | Email |  | No
comm-phase1-01-003 | 2026-05-14 | BP Targets team check-in invitation | Krishna | Doreen Larvie / Review Team | 2026-05-19 | Sent | Check-in email sent to understand progress, issues encountered, and support needs for the Blood pressure targets review. | task-phase1-01-004 | Validate abstract screening setup before screening starts | Email |  | No
comm-phase1-01-004 | 2026-05-27 | BP Targets abstract screening survey | Doreen Larvie / Krishna | Review Team | 2026-05-31 | Open | Abstract screening survey shared after AI-assisted screening completion | task-phase1-01-006 | Complete AI abstract screening survey | Email |  | Yes
comm-phase1-01-005 | 2026-05-27 | BP Targets human screening status | Doreen Larvie / Krishna | Doreen Larvie / Review Team | Immediate | Open | Asked team to confirm conventional human abstract screening status | task-phase1-01-007 | Confirm human screening status | Email |  | Yes
comm-phase1-01-006 | 2026-05-27 | BP Targets time log confirmation | Doreen Larvie / Krishna | Review Team | Immediate | Open | Asked team to confirm whether time taken was recorded | task-phase1-01-008 | Confirm time log | Email |  | Yes
Critical Items Displayed in Dashboard
CriticalItem | Severity | Owner | DueDate | Status | Notes | Display
Data items finalization recently resolved | Low |  |  | Open |  | Yes
Human abstract screening status not yet confirmed | High | Doreen Larvie / Review Team | Immediate | Open | Needed to confirm whether AI and conventional workflows are aligned before next stage | Yes
Abstract screening time log pending | Medium | Review Team | Immediate | Open | Required for study analysis and comparison | Yes

## phase1-02 Psoriasis
phase1-02 Psoriasis ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | phase1-02 | Yes
ShortName | Psoriasis | Yes
ReviewTitle | Systemic pharmacological treatments for chronic plaque psoriasis | Yes
Phase | Phase 1 | Yes
Status | Abstract Screening | Yes
Risk | Low | Yes
Tool | Nested Knowledge | Yes
Lead | Laurence Le Cleach / Sivem Afach | Yes
CurrentStage | Conventional title/abstract screening nearing completion; AI-assisted full-text selection almost complete; data extraction preparation/sample planning underway | Yes
CurrentUpdate | Conventional title/abstract screening is nearing completion; AI-assisted full-text selection is almost complete. The team is preparing a common sample of up to 10 studies for later data extraction. | Yes
NextAction | Complete conventional title/abstract screening; prepare common sample of up to 10 studies for later data extraction | Yes
TargetDate | TBD | Yes
Variance | Main workflow remains in abstract screening; data extraction is only in preparation/sample planning stage | Yes
Assessment | In Progress | Yes
DisplayInHTML | Yes | Yes | Set to No if review should not appear in dashboard.
LastUpdated | 2026-07-06 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding | Complete |  |  |  | Yes
setup | Complete |  |  |  | Yes
abstract | Active / nearing completion |  |  |  | Yes
fullText | AI-assisted full-text selection almost complete |  |  |  | Yes
extraction | Preparation only |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | Yes | Ready |  |  |  | Yes
PDFs | No | Not Started |  |  |  | Yes
Criteria | No | Not Started |  |  |  | Yes
Extraction | No | Not Started |  |  |  | Yes
Protocol | Yes | Ready |  |  |  | Yes
Time Log | Yes | Ready |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination | 0 | 0 | Not Started |  |  |  | Yes
Abstract Screening | 0 | 0 | Not Started |  |  |  | Yes
Full-text Screening | 0 | 0 | Not Started |  |  |  | Yes
Data Extraction / Analysis | 0 | 0 | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Complete |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Complete |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Complete |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Complete |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Complete |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Complete |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Complete |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Complete |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Complete |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Complete |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Complete |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Complete |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Complete |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Complete |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Complete |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Complete |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | In Progress |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Complete |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Complete |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Complete |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Complete |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Complete |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-phase1-02-001 | Confirm remaining full-text gaps with review team | Review Team / Meghan / Nested Knowledge | Waiting on Others | Medium | 2026-05-15 | Remaining unavailable or paywalled full texts | Nested Knowledge commented on unavailable or paywalled records; confirm whether review team can source remaining files. | Email | 2026-05-14 | No
task-phase1-02-002 | Confirm full-text readiness after Nested Knowledge fixes | Meghan / Response Team | In Progress | Medium | 2026-05-15 | Full-text files and criteria | Trial registry and multi-abstract PDF issues were addressed by Nested Knowledge; remaining access gaps need confirmation. | Email | 2026-05-14 | No
task-phase1-02-003 | Confirm full-text criteria and handling of remaining full-text issues | Review Team / Sean | Needs Action | Medium | 2026-05-15 | Eligibility criteria and full-text package | Confirm criteria before full-text AI setup proceeds. | MoM | 2026-05-10 | No
task-phase1-02-004 | Send usability survey after abstract screening completion | Krishna | Not Started | Low | After abstract screening | Abstract screening completion | Send survey when abstract screening is confirmed complete. | Project tracking | 2026-05-14 | No
task-phase1-02-005 | Confirm NK abstract screening survey responses | Susan / Ursula | Complete | Low | 2026-05-19 | NK abstract screening completion | Susan confirmed two new NK survey responses | Email | 2026-05-19 | Yes
task-phase1-02-006 | Finalize data item list for extraction | Sean / Sivem / Meghan | Complete | Medium | 2026-05-25 | Data extraction setup | Updated data item list uploaded to shared folder | Email | 2026-05-25 | Yes
task-phase1-02-007 | Enter data extraction fields into NK | Meghan / Response Team | In Progress | Medium | 2026-05-31 | Final data item list | Meghan confirmed she would start entering data fields into NK | Email | 2026-05-20 | Yes
task-phase1-02-008 | Confirm conventional extraction format | Emilie / Robin / Sean | In Progress | Medium | 2026-05-31 | Standalone data item definitions | Conventional team clarified expected Excel and Word outputs | Email | 2026-05-26 | Yes
task-phase1-02-009 | Confirm no further data item changes before AI extraction | Sean / Review Team | Pending | High | Immediate | NK setup completion | Sean asked extractors to follow agreed instructions before AI extraction begins | Email | 2026-05-27 | Yes
Recent Mail / Communication Log Displayed in Dashboard
CommunicationID | Date | Subject | People | Responsible | DueDate | Status | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
comm-phase1-02-001 | 2026-05-14 | Nested Knowledge full-text issue update | Ranita Tarchand | Nested Knowledge / Meghan / Review Team | 2026-05-15 | In Progress | Nested Knowledge completed action items #1 and #2 inside the Plaque Psoriasis project: trial registries with PDFs were added through CT.gov integration and multi-abstract PDFs were snipped to include the relevant abstract. | task-phase1-02-001 | Confirm remaining full-text gaps with review team | Email |  | No
comm-phase1-02-002 | 2026-05-14 | Remaining full-text access gaps | Ranita Tarchand | Review Team / Meghan | 2026-05-15 | Waiting on Others | Nested Knowledge reviewed records without full text and commented on records where a full text could not be sourced or was restricted behind a paywall. | task-phase1-02-001 | Confirm remaining full-text gaps with review team | Email |  | No
comm-phase1-02-003 | 2026-05-14 | Psoriasis team check-in invitation | Krishna | Laurence Le Cleach / Sivem Afach | 2026-05-19 | Sent | Check-in email sent to understand current progress, issues encountered, and support needs for the psoriasis review. | task-phase1-02-003 | Confirm full-text criteria and handling of remaining full-text issues | Email |  | No
| comm-phase1-02-004 | 2026-05-19 | Psoriasis / NK survey responses | Susan / Krishna | Susan / Ursula | 2026-05-19 | Complete | Two new NK title and abstract screening survey responses received | task-phase1-02-005 | Confirm survey responses | Email |  | Yes
| comm-phase1-02-005 | 2026-05-20 | Psoriasis NK data field setup | Meghan / Sivem / Sean | Meghan | 2026-05-31 | In Progress | Meghan confirmed she would start entering data fields into Nested Knowledge | task-phase1-02-007 | Enter NK data fields | Email |  | Yes
| comm-phase1-02-006 | 2026-05-25 | Psoriasis updated data item list | Sean / Sivem / Meghan | Sean / Meghan | 2026-05-25 | Complete | Updated data item list uploaded to shared folder | task-phase1-02-006 | Finalize data items | Email |  | Yes
| comm-phase1-02-007 | 2026-05-26 | Psoriasis conventional extraction format | Emilie / Sean / Meghan | Emilie / Robin | 2026-05-31 | In Progress | Conventional team clarified planned Excel and Word outputs | task-phase1-02-008 | Confirm conventional extraction format | Email |  | Yes
| comm-phase1-02-008 | 2026-05-27 | Psoriasis extraction definitions | Sean / Emilie / Meghan / Sivem | Review Team | Immediate | Open | Sean asked extractors to follow agreed definitions before AI extraction begins | task-phase1-02-009 | Confirm no further changes | Email |  | Yes
Critical Items Displayed in Dashboard
CriticalItem | Severity | Owner | DueDate | Status | Notes | Display
Remaining full-text gaps | Low |  |  | Open |  | No
Full-text criteria still need confirmation | Low |  |  | Open |  | No
Confirm no further data item changes before AI extraction | High | Sean / Review Team | Immediate | Open | Needed before AI-assisted data extraction begins in NK | Yes
Conventional extraction format alignment | Medium | Emilie / Robin / Sean | 2026-05-31 | In Progress | Conventional outputs need to match agreed standalone data item structure | Yes

## phase1-03 Fruit & Veg
phase1-03 Fruit & Veg ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | phase1-03 | Yes
ShortName | Fruit & Veg | Yes
ReviewTitle | Interventions for increasing fruit and vegetable consumption in children aged five years and under | Yes
Phase | Phase 1 | Yes
Status | AI-assisted abstract screening complete | Yes
Risk | Medium | Yes
Tool | Laser AI | Yes
Lead | Rebecca K. Hodder | Yes
CurrentStage | Laser AI abstract screening is complete. Fifteen studies have advanced to full-text screening. The conventional team is consolidating its abstract-screening results. | Yes
CurrentUpdate | Laser AI abstract screening is complete. Fifteen studies have advanced to full-text screening. The conventional team is consolidating its abstract-screening results. | Yes
NextAction | Complete the usability survey, await conventional-team consolidation, retrieve the PDFs for the 15 studies, and proceed with full-text screening setup. | Yes
TargetDate | TBD | Yes
Variance | The agreed decision-flow changes were initially not saved in Laser AI. Version 2 was subsequently applied, but earlier screened records may not include the comparator assessment; document this during the comparison. | Yes
Assessment | In Progress | Yes
DisplayInHTML | Yes | Yes | Set to No if review should not appear in dashboard.
LastUpdated | 2026-07-29 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding | Complete |  |  |  | Yes
setup | Complete |  |  |  | Yes
abstract | AI complete; conventional consolidation pending |  |  |  | Yes
fullText | 15 studies identified; PDF retrieval and full-text setup pending |  |  |  | Yes
extraction |  |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | Yes | Ready |  |  |  | Yes
PDFs | Pending | 15 full-text records identified; PDFs to be retrieved and uploaded |  |  |  | Yes
Criteria | Yes | Revised title/abstract decision flow saved as Version 2; full-text decision flow prepared |  |  |  | Yes
Extraction | No | Not Started |  |  |  | Yes
Protocol | No | Not Started |  |  |  | Yes
Time Log | No | Not Started |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination | 0 | 0 | Complete |  |  |  | Yes
Abstract Screening | 0 | 0 | AI complete; conventional consolidation pending |  |  |  | Yes
Full-text Screening | 0 | 0 | Setup pending for 15 studies |  |  |  | Yes
Data Extraction / Analysis | 0 | 0 | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Complete |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Complete |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Complete |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Complete |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Complete |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Complete |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Complete |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Under Review |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Complete |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Complete |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Under Review |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Under Review |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Under Review |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Complete |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Under Review |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-phase1-03-001 | Confirm allocated AI tool and review team access | Krishna / Response Team | Pending | Medium | 2026-05-20 | Tool allocation | Confirm logins and reviewer access before setup. | Project tracking | 2026-05-14 | No
task-phase1-03-002 | Arrange allocated tool training closer to study start date | Krishna / Tool Team | Not Started | Medium | Closer to start date | Tool allocation | Schedule training near active start. | Project tracking | 2026-05-14 | No
task-phase1-03-003 | Collect search results after 20 May search | Review Team | Waiting on Others | Medium | After 20 May | Search completion | Ask team to share RIS/search results after scheduled search. | Project tracking | 2026-05-14 | No
task-phase1-03-004 | Begin setup only after RIS and review materials are available | Response Team | Not Started | Medium | After materials received | RIS and review materials | Start setup only when materials are available. | Project tracking | 2026-05-14 | No
task-phase1-03-005 | Confirm Laser AI training completion | Rebecca / Kate / Laser AI | Complete | Low | 2026-05-27 | Training invite | Team proceeded with Laser AI training | Email | 2026-05-27 | Yes
task-phase1-03-006 | Schedule methodology re-onboarding | Gerald / Krishna / Review Team | Pending | Medium | This week | Krishna could not join tool training | Separate check-in needed to confirm workflow and methodology | Email | 2026-05-27 | Yes
task-phase1-03-007 | Confirm updated search completion | Rebecca / Kate | Pending | Medium | Immediate | Search run around 20 May | Need confirmation of final search status | Email | 2026-05-20 | Yes
task-phase1-03-008 | Confirm human abstract screening status | Rebecca / Kate | Pending | High | Immediate | Parallel workflow tracking | Need to confirm whether human screening started, postponed, or ongoing | Email | 2026-05-27 | Yes
task-phase1-03-009 | Confirm time recording | Rebecca / Kate | Pending | Medium | Immediate | Training/screening activity | Confirm training and screening time have been recorded | Email | 2026-05-27 | Yes
CommunicationID | Date | Subject | People | Responsible | DueDate | Status | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
comm-phase1-03-001 | 2026-05-08 | Fruit and vegetable search timing | Rebecca K. Hodder / Review Team | Krishna / Response Team | 2026-05-20 | Waiting on Others | Search is expected around 20 May; setup and training should be aligned closer to the active start date. | task-phase1-03-003 | Collect search results after 20 May search | Email |  | No
comm-phase1-03-002 | 2026-05-14 | Fruit and vegetable setup planning | Krishna | Review Team / Response Team | 2026-05-20 | Pending | Need to confirm allocated tool, review team access, and collect RIS/search results after the scheduled search. | task-phase1-03-001 | Confirm allocated AI tool and review team access | Project tracking |  | No
comm-phase1-03-004 | 2026-05-20 | Fruit & Veg updated search | Kate / Rebecca / Krishna | Rebecca / Kate | Immediate | Open | Kate informed that the updated search was being run and asked about training timing | task-phase1-03-007 | Confirm search completion | Email |  | Yes
comm-phase1-03-005 | 2026-05-26 | Fruit & Veg Laser AI training invite | Krishna / Rebecca / Kate | Rebecca / Kate | 2026-05-27 | Complete | Team was asked to confirm receipt of Laser AI training invite | task-phase1-03-005 | Confirm training completion | Email |  | Yes
comm-phase1-03-006 | 2026-05-26 | Rebecca team onboarding update | Krishna / Gerald | Gerald / Krishna | This week | Open | Gerald was informed that Laser AI session was scheduled for Rebecca and Kate’s team | task-phase1-03-006 | Schedule methodology re-onboarding | Email |  | Yes
comm-phase1-03-007 | 2026-05-27 | Laser AI training follow-up | Krishna / Kate / Rebecca | Krishna / Review Team | This week | Open | Krishna could not join due to 2 AM timing and noted that a separate check-in would be needed | task-phase1-03-006 | Arrange re-onboarding | Email |  | Yes
comm-phase1-03-008 | 2026-05-27 | Human screening status follow-up | Krishna / Rebecca / Kate | Rebecca / Kate | Immediate | Open | Human abstract screening status still needs confirmation for parallel workflow tracking | task-phase1-03-008 | Confirm human screening status | Email |  | Yes
Critical Items Displayed in Dashboard
CriticalItem | Severity | Owner | DueDate | Status | Notes | Display
CriticalItem | Severity | Owner | DueDate | Status | Notes | Display
Methodology re-onboarding still pending | Medium | Gerald / Krishna / Review Team | This week | Open | Needed because Krishna could not join the Laser AI tool training session | Yes
Human abstract screening status not confirmed | High | Rebecca / Kate | Immediate | Open | Needed to ensure AI-assisted and human workflows are tracked in parallel | Yes
Updated search completion not confirmed | Medium | Rebecca / Kate | Immediate | Open | Search was run around 20 May, but final completion/status needs confirmation | Yes

## phase1-04 Med Adherence
phase1-04 Med Adherence ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | phase1-04 | Yes
ShortName | Med Adherence | Yes
ReviewTitle | Interventions for improving medication-taking ability and adherence in older adults prescribed multiple medications | Yes
Phase | Phase 1 | Yes
Status | Withdrawn | Yes
Risk | Low | Yes
Tool | Nested Knowledge | Yes
Lead | Amanda Cross / Rehan Sarwar | Yes
CurrentStage | Team has withdrawn from the platform study due to capacity constraints | Yes
CurrentUpdate | Team has withdrawn from the platform study due to capacity constraints | Yes
NextAction | Retain as withdrawn/historical record; no active follow-up required | Yes
TargetDate |  | Yes
Variance | Withdrawn due to team capacity constraints | Yes
Assessment | Withdrawn | Yes
DisplayInHTML | No | No | Set to No if review should not appear in dashboard.
LastUpdated | 2026-07-06 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding | Withdrawn |  |  |  | Yes
setup |  |  |  |  | Yes
abstract |  |  |  |  | Yes
fullText |  |  |  |  | Yes
extraction |  |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | No | Not Started |  |  |  | Yes
PDFs | No | Not Started |  |  |  | Yes
Criteria | No | Not Started |  |  |  | Yes
Extraction | No | Not Started |  |  |  | Yes
Protocol | No | Not Started |  |  |  | Yes
Time Log | No | Not Started |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination | 0 | 0 | Not Started |  |  |  | Yes
Abstract Screening | 0 | 0 | Not Started |  |  |  | Yes
Full-text Screening | 0 | 0 | Not Started |  |  |  | Yes
Data Extraction / Analysis | 0 | 0 | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Under Review |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Not Started |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Not Started |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Not Started |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Not Started |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Not Started |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Not Started |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Not Started |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Not Started |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Not Started |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Not Started |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Not Started |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Not Started |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Not Started |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-phase1-04-001 | Confirm review eligibility and participation | Core Team / Review Team | Under Review | High | 2026-05-15 | Review confirmation | Confirm whether this review can be included in Phase 1. | Project tracking | 2026-05-14 | Yes
task-phase1-04-002 | Confirm review timeline and start date | Krishna / Review Team | Pending | Medium | TBD | Team availability | Agree realistic start date only if review is confirmed. | Project tracking | 2026-05-14 | Yes
task-phase1-04-003 | Confirm allocated AI tool after eligibility decision | Core Team | Pending | Medium | TBD | Eligibility decision | Assign one AI tool only after eligibility and participation are confirmed. | Project tracking | 2026-05-14 | Yes
task-phase1-04-004 | Hold setup materials request until confirmation | Krishna / Review Team | Not Started | Low | After confirmation | Eligibility and allocation | Do not request RIS, PDFs, criteria, or extraction materials until the review is confirmed. | Project tracking | 2026-05-14 | Yes
Recent Mail / Communication Log Displayed in Dashboard
CommunicationID | Date | Subject | People | Responsible | DueDate | Status | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
comm-phase1-04-001 | 2026-05-08 | Chlamydia candidate tracking | Elena Kostov / Core Team | Krishna / Gerald / Ella | 2026-05-15 | Under Review | Screening for genital chlamydia infection remains under review as a possible Phase 1 review. Eligibility, participation, timeline, and tool allocation need confirmation before setup. | task-phase1-04-001 | Confirm review eligibility and participation | Email |  | Yes
Critical Items Displayed in Dashboard
CriticalItem | Severity | Owner | DueDate | Status | Notes | Display
Eligibility and participation not confirmed | High |  |  | Open |  | Yes

## Resources
Resources
ResourceID | ResourceName | Description | ResourceType | URL | Owner | LinkedPhase | LinkedReviewID | Status | DisplayInHTML | DisplayOrder | LastUpdated | InternalNotes
res-001 | General information folder | Shared folder with onboarding and scope documents. | Folder | https://example.com/general-folder | Krishna | Phase 1 | All | Active | Yes | 1 | 2026-05-14
res-002 | Scope document | Protocol/scope document for the study. | PDF | https://example.com/scope | Krishna | Phase 1 | All | Active | Yes | 2 | 2026-05-14
res-003 | Review team onboarding slides | Presentation shared with review teams. | Presentation | https://example.com/onboarding | Krishna | Phase 1 | All | Active | Yes | 3 | 2026-05-14

## phase1-05 Vitamin C
phase1-05 Vitamin C ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | phase1-05 | Yes
ShortName | Vitamin C | Yes
ReviewTitle | Vitamin C supplementation for prevention and treatment of pneumonia | Yes
Phase | Phase 1 | Yes
Status | Setup phase | Yes
Risk | Medium | Yes
Tool | Laser AI | Yes
Lead | Syeda Kanza Naqvi / Jai Das | Yes
CurrentStage | Setup phase underway; Laser AI allocated; search/LILACS clarification and remaining setup materials are being finalized; abstract screening has not yet commenced | Yes
CurrentUpdate | Vitamin C is in the setup phase with Laser AI allocated. Search/LILACS clarification and remaining setup materials are being finalized; abstract screening has not yet commenced. | Yes
NextAction | Complete setup materials and Laser AI configuration before commencing abstract screening | Yes
TargetDate | TBD | Yes
Variance | Screening start depends on completion of setup materials and Laser AI configuration | Yes
Assessment | In Progress | Yes
DisplayInHTML | Yes | Yes | Set to No if review should not appear in dashboard.
LastUpdated | 2026-07-06 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding | Complete |  |  |  | Yes
setup | Pending |  |  |  | Yes
abstract | Not Started |  |  |  | Yes
fullText |  |  |  |  | Yes
extraction |  |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | Partial | LILACS/search support ongoing |  |  |  | Yes
PDFs | No | Not Started |  |  |  | Yes
Criteria | Pending | Awaiting final materials |  |  |  | Yes
Extraction | No | Not Started |  |  |  | Yes
Protocol | No | Not Started |  |  |  | Yes
Time Log | No | Not Started |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination | 0 | 0 | Not Started |  |  |  | Yes
Abstract Screening | 0 | 0 | Not Started |  |  |  | Yes
Full-text Screening | 0 | 0 | Not Started |  |  |  | Yes
Data Extraction / Analysis | 0 | 0 | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Complete |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Complete |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Complete |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Complete |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Not Started |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Complete |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Under Review |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Under Review |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Not Started |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Not Started |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Not Started |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Not Started |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Not Started |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Not Started |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Not Started |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-phase1-05-001 | Identify additional eligible review | Core Team | Under Review | High | 2026-05-19 | Candidate pool | Shortlist review options. | Project tracking | 2026-05-14 | Yes
task-phase1-05-002 | Confirm team availability after candidate selection | Krishna / Review Team | Not Started | Medium | TBD | Review identification | Contact review team once candidate is selected. | Project tracking | 2026-05-14 | Yes
task-phase1-05-003 | Assign allocated AI tool after candidate selection | Core Team | Not Started | Medium | TBD | Tool allocation | Assign one tool only after a review is selected. | Project tracking | 2026-05-14 | Yes
task-phase1-05-004 | Hold onboarding until review is confirmed | Krishna / Response Team | Not Started | Low | After confirmation | Review and tool confirmation | Start onboarding only after candidate and tool are confirmed. | Project tracking | 2026-05-14 | Yes
Recent Mail / Communication Log Displayed in Dashboard
CommunicationID | Date | Subject | People | Responsible | DueDate | Status | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
comm-phase1-05-001 | 2026-05-14 | Additional Phase 1 review slot | Core Team | Krishna / Core Team | 2026-05-19 | Under Review | One additional eligible review still needs to be identified or confirmed for Phase 1. | task-phase1-05-001 | Identify additional eligible review | Project tracking |  | Yes
Critical Items Displayed in Dashboard
CriticalItem | Severity | Owner | DueDate | Status | Notes | Display
Open Phase 1 review slot | High |  |  | Open |  | Yes

## phase2-01 Phase 2 Batch
phase2-01 Phase 2 Batch ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | phase2-01 | Yes
ShortName | Phase 2 Batch | Yes
ReviewTitle | Phase 2 Batch | Yes
Phase | Phase 2 | Yes
Status | Scheduled | Yes
Risk | Medium | Yes
Tool | TBD | Yes
Lead | TBD | Yes
CurrentStage | Future batch planning | Yes
CurrentUpdate | No update recorded. | Yes
NextAction | Keep placeholders until Phase 1 stabilizes. | Yes
TargetDate | TBD | Yes
Variance | Phase 2 depends on Phase 1 stabilization and lessons learned. | Yes
Assessment | Not Started | Yes
DisplayInHTML | Yes | Yes | Set to No if review should not appear in dashboard.
LastUpdated | 2026-05-14 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding |  |  |  |  | Yes
setup |  |  |  |  | Yes
abstract |  |  |  |  | Yes
fullText |  |  |  |  | Yes
extraction |  |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | No | Not Started |  |  |  | Yes
PDFs | No | Not Started |  |  |  | Yes
Criteria | No | Not Started |  |  |  | Yes
Extraction | No | Not Started |  |  |  | Yes
Protocol | No | Not Started |  |  |  | Yes
Time Log | No | Not Started |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination | 0 | 0 | Not Started |  |  |  | Yes
Abstract Screening | 0 | 0 | Not Started |  |  |  | Yes
Full-text Screening | 0 | 0 | Not Started |  |  |  | Yes
Data Extraction / Analysis | 0 | 0 | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Not Started |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Not Started |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Not Started |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Not Started |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Not Started |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Not Started |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Not Started |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Not Started |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Not Started |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Not Started |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Not Started |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Not Started |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Not Started |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Not Started |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-phase2-01-001 | Keep Phase 2 placeholder until Phase 1 stabilizes | Krishna / Core Team | Scheduled | Medium | After Phase 1 | Phase 1 lessons learned | Use Phase 1 lessons before scaling Phase 2. | Project tracking | 2026-05-14 | Yes
Recent Mail / Communication Log Displayed in Dashboard
CommunicationID | Date | Subject | People | Responsible | DueDate | Status | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
No
Critical Items Displayed in Dashboard
CriticalItem | Severity | Owner | DueDate | Status | Notes | Display
No

## New_Reviews
New Reviews Pipeline ¦ Continuous Onboarding
Use this sheet to capture candidate reviews before they are converted into full review sheets. Keep it light: review name, category/status, target phase, owner, and remarks.
Pipeline Summary
Shortlisted
Under Shortlisting
Future Phase
Not Eligible
CandidateID | ReviewName | Category | Status | TargetPhase | Lead/Contact | ExpectedTiming | Remarks | MoveToFullSheet | Display
new-01 | Mohan Pammi — Human milk-derived fortifier versus bovine milk-derived fortifier for prevention of mortality and morbidity in preterm neonates | Converted to full sheet | Participation confirmed; team roles agreed; onboarding and study material collection underway; tool training pending | Phase 1 | Mohan Pammi | Onboarding and study material collection underway | Converted to phase1-07 Human Milk; Nested Knowledge allocated; tool training pending | Yes | No
new-02 | Amanda Cross ? Interventions for improving medication-taking ability and adherence in older adults prescribed multiple medications | Withdrawn | Team has withdrawn from the platform study due to capacity constraints | Phase 1 | Amanda Cross / Rehan Sarwar | 2026-06-08 | Withdrawn due to capacity constraints; retain as historical record | No | Yes
new-03 | Jai Das — Preventive lipid-based nutrient supplements given with complementary foods to infants and young children 6 to 23 months of age for health, nutrition, and developmental outcomes | Under Shortlisting | Search by July 2026 | Phase 1 |  |  |  | No | Yes
new-04 | Jai Das — Vitamin C supplementation for prevention and treatment of pneumonia | Converted to full sheet | Tracked as phase1-05 | Phase 1 | Syeda Kanza Naqvi / Jai Das | Search update in progress | Final updated search/RIS and remaining study materials pending; Sean supporting LILACS/search issue | Yes | No
[8 empty] | No | No
new-06 | Lesly Chavez Rimache / Cochrane Peru | Future Phase | Two systematic review proposals have been submitted to Cochrane, but they are still awaiting evaluation/acceptance and are not yet at protocol/search stage.
new-07 | Minyahil Tadesse / Cochrane Ethiopia | Future Phase | Two Cochrane protocols have been published, but the full review work/searches have not yet started
new-08 | Francesco Nonino | Future Phase | No suitable updates are currently available, but he will monitor and share any potential review updates later this year.
new-09 | Giulio Cherubini — Impact of Manual Therapy on Instrumentalist Musicians With Playing-Related Musculoskeletal Disorders: A Systematic Review | Not Eligible | Non-Cochrane review
new-10 | Francesca Cecchi / Giulio Cherubini — Effects of lower limb botulinum toxin injections on gait functional outcomes in stroke survivors | Not Eligible | Non-Cochrane review
new-11 | Feng Sun / Zuhaer — Automated Insulin Delivery Systems in Children and Adolescents With Type 1 Diabetes | Not Eligible | Non-Cochrane review
new-12 | Patricia Clark — Effectiveness and safety of pharmacological interventions for the primary prevention of osteoporosis in postmenopausal women | Not Eligible | Independent/non-Cochrane review
new-13 | Alison Edelman — Meningioma and hormonal contraceptives | Not Eligible | Currently planned outside Cochrane
new-14 | Elena Kostova — Screening for genital chlamydia infection | Not Eligible | Cochrane review update, but not eligible because abstract screening had already started and more than half of the records had already been screened. The team also could not meet the required parallel workflow structure.
new-15 | Patricia C. Heyn — Aerobic and Resistance Training Interventions for Cognitive Outcomes in Older Adults with Mild Cognitive Impairment and Alzheimer's Disease and Related Dementias: An Umbrella Review of Meta-Analyses of Randomized Trials | Not Eligible | Not eligible because it is not a Cochrane review update and most methods are already completed, with the team validating the database and starting analysis.
new-16 | Zuhaer / Feng Sun — Gas gangrene Cochrane Review update | Not Eligible | Not eligible for the current phase because the team is considering expanding the scope to include observational studies, which would require a major methodological change and may not align with the current validation workflow/timeline.
new-17 | Jeremy Steen / Bradley Johnston - Probiotics for the prevention of paediatric antibiotic-associated diarrhoea | Converted to full sheet | Onboarding and tool training completed; awaiting final template revisions | Phase 1 | Jeremy Steen / Bradley Johnston | Awaiting final template revisions | Converted to phase1-06 Probiotics; Nested Knowledge allocated | Yes | No
new-18 | Anna Rogers - Abdominal Irrigation at Caesarean Section | Withdrawn | Team has withdrawn from the platform study and will not be participating | Phase 1 | Anna Rogers | Not participating | Withdrawn; no active follow-up | No | No
Suggested use of categories
Shortlisted | Likely eligible and suitable for near-term onboarding. Use when only final confirmation or timing is pending.
Under Shortlisting | Still being assessed. Use when eligibility, team capacity, timeline, or workflow fit needs clarification.
Future Phase | Potentially useful but not for current onboarding wave. Keep for Phase 2 or later pipeline planning.
Not Eligible | Not suitable for the current validation phase. Keep brief reason in Remarks.

## Workflow_Master
Workflow Master
Use row 4 onward for data entry. Keep IDs stable for GitHub/data.js export.
WorkflowStepID | StepOrder | WorkflowGroup | ShortName | FullActivity | ResponsibleDefault | DependsOn | Blocks | DefaultStatus | DisplayInHTML | DisplayOrder | InternalNotes
w01 | 1 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Not Started | Yes | 1
w02 | 2 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Not Started | Yes | 2
w03 | 3 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Not Started | Yes | 3
w04 | 4 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Not Started | Yes | 4
w05 | 5 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Not Started | Yes | 5
w06 | 6 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Not Started | Yes | 6
w07 | 7 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Not Started | Yes | 7
w08 | 8 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Not Started | Yes | 8
w09 | 9 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started | Yes | 9
w10 | 10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Not Started | Yes | 10
w11 | 11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Not Started | Yes | 11
w12 | 12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Not Started | Yes | 12
w13 | 13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Not Started | Yes | 13
w14 | 14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Not Started | Yes | 14
w15 | 15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Not Started | Yes | 15
w16 | 16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Not Started | Yes | 16
w17 | 17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started | Yes | 17
w18 | 18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started | Yes | 18
w19 | 19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started | Yes | 19
w20 | 20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started | Yes | 20
w21 | 21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started | Yes | 21
w22 | 22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started | Yes | 22
w23 | 23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started | Yes | 23
w24 | 24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started | Yes | 24
w25 | 25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started | Yes | 25
w26 | 26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started | Yes | 26
w27 | 27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started | Yes | 27
w28 | 28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started | Yes | 28
w29 | 29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started | Yes | 29
w30 | 30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started | Yes | 30
w31 | 31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started | Yes | 31
w32 | 32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started | Yes | 32
w33 | 33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started | Yes | 33
w34 | 34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started | Yes | 34
w35 | 35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started | Yes | 35
w36 | 36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started | Yes | 36
w37 | 37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started | Yes | 37
w38 | 38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started | Yes | 38
w39 | 39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started | Yes | 39
w40 | 40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started | Yes | 40
w41 | 41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started | Yes | 41
w42 | 42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started | Yes | 42
w43 | 43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started | Yes | 43
w44 | 44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started | Yes | 44
w45 | 45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started | Yes | 45
w46 | 46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started | Yes | 46
w47 | 47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started | Yes | 47
w48 | 48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started | Yes | 48
w49 | 49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started | Yes | 49
w50 | 50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started | Yes | 50
w51 | 51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started | Yes | 51
w52 | 52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started | Yes | 52
w53 | 53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started | Yes | 53
w54 | 54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started | Yes | 54
w55 | 55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started | Yes | 55
w56 | 56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started | Yes | 56
w57 | 57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started | Yes | 57
w58 | 58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started | Yes | 58
w59 | 59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started | Yes | 59
w60 | 60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started | Yes | 60
w61 | 61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started | Yes | 61
w62 | 62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started | Yes | 62
w63 | 63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started | Yes | 63

## Upcoming_Meetings
MeetingID | Date | ETTime | UKTime | Title | Purpose | People | Owner | LinkedPhase | Status | LinkedReviewID | MeetingLink | Display
mtg-01 | 2026-06-08 | 2:00-3:00 AM EDT | 7:00-8:00 AM BST | NK Training - Medication Adherence | CDT calendar time: Jun 8, 1:00-2:00 AM. Nested Knowledge training for Medication Adherence. | Amanda Cross / Rehan Sarwar / Krishna / Nested Knowledge | Krishna | Phase 1 | Scheduled | phase1-04 |  | No
mtg-02 | 2026-06-08 | 3:00-4:00 AM EDT | 8:00-9:00 AM BST | Onboarding - Medication Adherence | CDT calendar time: Jun 8, 2:00-3:00 AM. Onboarding and split-team workflow confirmation. | Amanda Cross / Rehan Sarwar / Krishna | Krishna | Phase 1 | Scheduled | phase1-04 |  | No
mtg-03 | 2026-06-12 | 5:00-6:00 AM EDT | 10:00-11:00 AM BST | Vitamin C Onboarding | CDT calendar time: Jun 12, 4:00-5:00 AM. Review onboarding for Vitamin C. | Jai Das / Krishna / Core Team | Krishna | Phase 1 | Scheduled | phase1-05 |  | No
mtg-05 |  |  |  | Fruit & Veg Re-onboarding | Re-onboarding meeting for Fruit & Veg; time TBD. | Rebecca K. Hodder / Krishna / Core Team | Krishna | Phase 1 | Scheduled | phase1-03 |  | Yes
mtg-06 |  |  |  | NK Training - Human Milk Fortifier | Nested Knowledge training for Human Milk Fortifier; time TBD. | Mohan Pammi / Krishna / Nested Knowledge | Krishna | Phase 1 | Scheduled | phase1-07 |  | Yes
mtg-07 |  |  |  | Human Milk Fortifier Onboarding | Onboarding meeting for Human Milk Fortifier; time TBD. | Mohan Pammi / Krishna / Core Team | Krishna | Phase 1 | Scheduled | phase1-07 |  | Yes
mtg-04 | 2026-06-08 | 10:00-11:00 AM EDT | 3:00-4:00 PM BST | AI Pilot Core Project Team Catch-up | CDT calendar time: 9:00-10:00 AM. Core project team catch-up. | Core Project Team | Krishna | Project coordination | Scheduled |  |  | No

## phase1-06 Probiotics
phase1-06 Probiotics ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | phase1-06 | Yes
ShortName | Probiotics AAD | Yes
ReviewTitle | Probiotics for the prevention of paediatric antibiotic-associated diarrhoea | Yes
Phase | Phase 1 | Yes
Status | Onboarded / awaiting template revisions | Yes
Risk | Medium | Yes
Tool | Nested Knowledge | Yes
Lead | Jeremy Steen / Bradley Johnston | Yes
CurrentStage | Onboarding and tool training completed; RIS file, protocol, eligibility criteria, and draft data extraction template received | Yes
CurrentUpdate | RIS file, protocol, eligibility criteria, and draft data extraction template received; awaiting final template revisions before project configuration and screening begin | Yes
NextAction | Await final template revisions before project configuration and screening begin | Yes
TargetDate | TBD | Yes
Variance | Project configuration and screening depend on final data extraction template revisions | Yes
Assessment | In Progress | Yes
DisplayInHTML | Yes | Yes | Set to No if review should not appear in dashboard.
LastUpdated | 2026-07-06 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding | Complete |  |  |  | Yes
setup | Awaiting final template revisions |  |  |  | Yes
abstract | Not Started |  |  |  | Yes
fullText | Not Started |  |  |  | Yes
extraction | Draft template received |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | Yes | Received |  |  |  | Yes
PDFs | No | Not Started |  |  |  | Yes
Criteria | Yes | Received |  |  |  | Yes
Extraction | Yes | Received |  |  |  | Yes
Protocol | Draft | Awaiting final template revisions |  |  |  | Yes
Time Log | No | Not Started |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination |  |  | Not Started |  |  |  | Yes
Abstract Screening |  |  | Not Started |  |  |  | Yes
Full-text Screening |  |  | Not Started |  |  |  | Yes
Data Extraction / Analysis |  |  | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Complete |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Complete |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Complete |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Complete |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Complete |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Complete |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Complete |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Under Review |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Complete |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Complete |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Under Review |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Under Review |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Under Review |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Under Review |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Not Started |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-phase1-05-001 | Identify additional eligible review | Core Team | Under Review | High | 2026-05-19 | Candidate pool | Shortlist review options. | Project tracking | 2026-05-14 | Yes
task-phase1-05-002 | Confirm team availability after candidate selection | Krishna / Review Team | Not Started | Medium | TBD | Review identification | Contact review team once candidate is selected. | Project tracking | 2026-05-14 | Yes
task-phase1-05-003 | [6 empty] | Assign one tool only after a review is selected. | Project tracking | 2026-05-14 | Yes
task-phase1-05-004 | [6 empty] | Start onboarding only after candidate and tool are confirmed. | Project tracking | 2026-05-14 | Yes
Recent Mail / Communication Log Displayed in Dashboard
CommunicationID | [6 empty] | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
comm-phase1-05-001 | [6 empty] | One additional eligible review still needs to be identified or confirmed for Phase 1. | task-phase1-05-001 | Identify additional eligible review | Project tracking |  | Yes
Critical Items Displayed in Dashboard
CriticalItem
Open Phase 1 review slot

## phase1-07 Human Milk
phase1-07 Human Milk ¦ Dashboard Content Sheet
Executive Review Card
Card Field | Value | Display | Notes
ReviewID | phase1-07 | Yes
ShortName | Human Milk Fortifier | Yes
ReviewTitle | Human milk-derived versus bovine milk-derived fortifier for prevention of mortality and morbidity in preterm neonates | Yes
Phase | Phase 1 | Yes
Status | Onboarding / materials collection | Yes
Risk | Medium | Yes
Tool | Nested Knowledge | Yes
Lead | Mohan Pammi | Yes
CurrentStage | Participation confirmed; team roles agreed; onboarding and study material collection underway; tool training pending | Yes
CurrentUpdate | Participation confirmed; team roles agreed; study material collection and onboarding are underway | Yes
NextAction | Collect study materials, complete Nested Knowledge tool training, and configure project for screening | Yes
TargetDate | TBD | Yes
Variance | Tool training and project configuration pending | Yes
Assessment | In Progress | Yes
DisplayInHTML | Yes | Yes | Set to No if review should not appear in dashboard.
LastUpdated | 2026-07-06 | Yes
Dashboard Milestones
Milestone | Status | Owner | TargetDate | Notes | Display
onboarding | Underway |  |  |  | Yes
setup | Pending |  |  |  | Yes
abstract | Not Started |  |  |  | Yes
fullText | Not Started |  |  |  | Yes
extraction | Not Started |  |  |  | Yes
analysis |  |  |  |  | Yes
Files Displayed in Review Detail
FileType | Ready | Status | Owner | DueDate | Notes | Display
RIS | Pending | Study materials collection underway |  |  |  | Yes
PDFs | Pending | Study materials collection underway |  |  |  | Yes
Criteria | Pending | Study materials collection underway |  |  |  | Yes
Extraction | Pending | Study materials collection underway |  |  |  | Yes
Protocol | Pending | Study materials collection underway |  |  |  | Yes
Time Log | No | Not Started |  |  |  | Yes
Stage Progress: Visual Tracker / Operations
StageName | HumanProgress | AIProgress | Status | Owner | TargetDate | Notes | Display
Setup / Coordination |  |  | Not Started |  |  |  | Yes
Abstract Screening |  |  | Not Started |  |  |  | Yes
Full-text Screening |  |  | Not Started |  |  |  | Yes
Data Extraction / Analysis |  |  | Not Started |  |  |  | Yes
Review Workflow Status: Full 63 Actions
ActionOrder | WorkflowStepID | WorkflowGroup | ShortName | Activity | Responsible | DependsOn | Blocks | Status | Owner | DueDate | Notes | Display
1 | w01 | Review selection and onboarding | Review selected | Selection of review - core team | Core Team |  | w02 | Complete |  |  |  | Yes
2 | w02 | Review selection and onboarding | PM confirmation | Selection of review - project manager confirmation | Krishna | w01 | w03 | Complete |  |  |  | Yes
3 | w03 | Review selection and onboarding | Final confirmation | Selection of review - final confirmation | Krishna | w02 | w04 | Complete |  |  |  | Yes
4 | w04 | Review selection and onboarding | Tool allocated | Confirm allocated AI tool for review | Core Team | w03 | w05,w07,w15,w30,w45 | Complete |  |  |  | Yes
5 | w05 | Review selection and onboarding | Team split | Confirm review team split: Human workflow and AI-assisted workflow | Krishna / Review Team | w04 | w08,w09,w17,w32,w47 | Complete |  |  |  | Yes
6 | w06 | Review selection and onboarding | Folder access | Confirm SharePoint/folder access for review team | Krishna / Review Team | w03 | w10,w11,w12 | Under Review |  |  |  | Yes
7 | w07 | Review selection and onboarding | Tool access | Confirm AI tool access for allocated users | Response Team / Allocated Tool Team | w04 | w15,w30,w45 | Not Started |  |  |  | Yes
8 | w08 | Review selection and onboarding | Blinding shared | Confirm blinding instructions shared with review teams | Krishna / Sean | w05 | w17,w18,w32,w33,w47,w48 | Under Review |  |  |  | Yes
9 | w09 | Review selection and onboarding | Time tracking | Confirm Clockify or alternate time-tracking setup | Krishna | w05 | w17,w18,w32,w33,w47,w48 | Not Started |  |  |  | Yes
10 | w10 | Setup package and data item readiness | RIS files | Review team to share RIS files with setup team | Review Team | w06 | w15 | Not Started |  |  |  | Yes
11 | w11 | Setup package and data item readiness | Protocol & criteria | Review team to share protocol and inclusion/exclusion criteria | Review Team | w06 | w12,w15,w29 | Not Started |  |  |  | Yes
12 | w12 | Setup package and data item readiness | Data items | Finalise data items with Sean | Review Team / Sean | w11 | w13,w14,w43,w44 | Not Started |  |  |  | Yes
13 | w13 | Setup package and data item readiness | Comparable DE | Confirm data extraction structure is comparable between Human and AI workflows | Review Team / Sean | w12 | w14,w44 | Not Started |  |  |  | Yes
14 | w14 | Setup package and data item readiness | Sean approval | Confirm extraction form/template is approved by Sean | Sean | w13 | w43,w44,w45 | Not Started |  |  |  | Yes
15 | w15 | Abstract screening | Tool setup | Tool setup - allocated AI tool for abstract screening | Response Team / Allocated Tool Team | w04,w07,w10,w11 | w16 | Not Started |  |  |  | Yes
16 | w16 | Abstract screening | Setup validated | Review team validates abstract screening setup before starting | Review Team | w15 | w17,w18 | Not Started |  |  |  | Yes
17 | w17 | Abstract screening | Human screening | Abstract screening - Human workflow | Review Team | w05,w08,w09,w16 | w21,w24,w25 | Not Started |  |  |  | Yes
18 | w18 | Abstract screening | AI screening | Abstract screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w16 | w19,w21,w24,w25 | Not Started |  |  |  | Yes
19 | w19 | Abstract screening | Export AI output | Export abstract screening output from allocated AI tool | Allocated Tool Team | w18 | w20 | Not Started |  |  |  | Yes
20 | w20 | Abstract screening | Share output | Share abstract screening output with Sean / data manager | Krishna / Data Manager | w19 | w24,w25 | Not Started |  |  |  | Yes
21 | w21 | Abstract screening | Survey sent | Share usability survey on abstract screening experience | Krishna | w17,w18 | w22 | Not Started |  |  |  | Yes
22 | w22 | Abstract screening | Survey submitted | Submit usability survey on abstract screening experience | Review Team | w21 | w23 | Not Started |  |  |  | Yes
23 | w23 | Abstract screening | Survey received | Confirm usability survey responses received for abstract screening | Krishna | w22 | w24 | Not Started |  |  |  | Yes
24 | w24 | Abstract screening | Quality check | Data completeness and quality check before abstract screening adjudication | Data Manager / Sean | w20,w23 | w25 | Not Started |  |  |  | Yes
25 | w25 | Abstract screening | Abstract adjudication | Adjudication panel after abstract screening | Sean and Adjudication Panel | w24 | w26,w28,w30 | Not Started |  |  |  | Yes
26 | w26 | Full-text readiness and screening | PDFs received | Review team to share PDF files with setup team | Review Team | w25 | w27,w29 | Not Started |  |  |  | Yes
27 | w27 | Full-text readiness and screening | PDF issues logged | Confirm unavailable PDFs or access issues are logged | Review Team / Krishna | w26 | w29 | Not Started |  |  |  | Yes
28 | w28 | Full-text readiness and screening | Check-in meeting | Meeting with Gerald, Amin, Susan, and optional review team members | Krishna | w25 | w29 | Not Started |  |  |  | Yes
29 | w29 | Full-text readiness and screening | Criteria finalized | Confirm full-text screening criteria are finalized | Review Team / Sean | w11,w26,w27,w28 | w30 | Not Started |  |  |  | Yes
30 | w30 | Full-text readiness and screening | Tool setup | Tool setup - allocated AI tool for full-text screening | Response Team / Allocated Tool Team | w04,w07,w29 | w31 | Not Started |  |  |  | Yes
31 | w31 | Full-text readiness and screening | Setup validated | Review team validates full-text screening setup before starting | Review Team | w30 | w32,w33 | Not Started |  |  |  | Yes
32 | w32 | Full-text readiness and screening | Human full text | Full-text screening - Human workflow | Review Team | w05,w08,w09,w31 | w36,w39,w40 | Not Started |  |  |  | Yes
33 | w33 | Full-text readiness and screening | AI full text | Full-text screening - allocated AI tool | Allocated Tool Team | w07,w08,w09,w31 | w34,w36,w39,w40 | Not Started |  |  |  | Yes
34 | w34 | Full-text readiness and screening | Export AI output | Export full-text screening output from allocated AI tool | Allocated Tool Team | w33 | w35 | Not Started |  |  |  | Yes
35 | w35 | Full-text readiness and screening | Share output | Share full-text screening output with Sean / data manager | Krishna / Data Manager | w34 | w39,w40 | Not Started |  |  |  | Yes
36 | w36 | Full-text readiness and screening | Survey sent | Share usability survey on full-text screening workflow | Krishna | w32,w33 | w37 | Not Started |  |  |  | Yes
37 | w37 | Full-text readiness and screening | Survey submitted | Submit usability survey on full-text screening workflow | Review Team | w36 | w38 | Not Started |  |  |  | Yes
38 | w38 | Full-text readiness and screening | Survey received | Confirm usability survey responses received for full-text screening | Krishna | w37 | w39 | Not Started |  |  |  | Yes
39 | w39 | Full-text readiness and screening | Quality check | Data completeness and quality check before full-text adjudication | Data Manager / Sean | w35,w38 | w40 | Not Started |  |  |  | Yes
40 | w40 | Full-text readiness and screening | Full-text adjudication | Adjudication panel after full-text screening | Sean and Adjudication Panel | w39 | w42,w43,w45 | Not Started |  |  |  | Yes
41 | w41 | Data extraction | Platform ready | Finalisation of Laser AI platform/server setup, if applicable | Core Team / Laser AI | w04,w07 | w45 | Not Started |  |  |  | Yes
42 | w42 | Data extraction | DE check-in | Meeting with Gerald and optional review team members before data extraction | Krishna | w40 | w43 | Not Started |  |  |  | Yes
43 | w43 | Data extraction | DE items confirmed | Confirm final data extraction items and definitions | Review Team / Sean | w12,w14,w40,w42 | w44 | Not Started |  |  |  | Yes
44 | w44 | Data extraction | Form approved | Confirm extraction form/template is approved by Sean | Sean | w13,w14,w43 | w45 | Not Started |  |  |  | Yes
45 | w45 | Data extraction | Tool setup | Tool setup - allocated AI tool for data extraction | Response Team / Allocated Tool Team | w41,w44 | w46 | Not Started |  |  |  | Yes
46 | w46 | Data extraction | Setup validated | Review team validates data extraction setup before starting | Review Team | w45 | w47,w48 | Not Started |  |  |  | Yes
47 | w47 | Data extraction | Human extraction | Data extraction - Human workflow | Review Team | w05,w08,w09,w46 | w51,w54,w55 | Not Started |  |  |  | Yes
48 | w48 | Data extraction | AI extraction | Data extraction - allocated AI tool | Allocated Tool Team | w07,w08,w09,w46 | w49,w51,w54,w55 | Not Started |  |  |  | Yes
49 | w49 | Data extraction | Export AI output | Export data extraction output from allocated AI tool | Allocated Tool Team | w48 | w50 | Not Started |  |  |  | Yes
50 | w50 | Data extraction | Share output | Share data extraction output with Sean / data manager | Krishna / Data Manager | w49 | w54,w55 | Not Started |  |  |  | Yes
51 | w51 | Data extraction | Survey sent | Share usability survey on data extraction workflow | Krishna | w47,w48 | w52 | Not Started |  |  |  | Yes
52 | w52 | Data extraction | Survey submitted | Submit usability survey on data extraction workflow | Review Team | w51 | w53 | Not Started |  |  |  | Yes
53 | w53 | Data extraction | Survey received | Confirm usability survey responses received for data extraction | Krishna | w52 | w54 | Not Started |  |  |  | Yes
54 | w54 | Data extraction | Quality check | Data completeness and quality check before data extraction adjudication | Data Manager / Sean | w50,w53 | w55 | Not Started |  |  |  | Yes
55 | w55 | Data extraction | Adjudication dataset | Prepare adjudication-ready dataset | Data Manager / Sean | w54 | w56,w57,w58,w61,w62,w63 | Not Started |  |  |  | Yes
56 | w56 | Data extraction | DE adjudication | Adjudication panel after data extraction | Sean and Adjudication Panel | w55 | w57,w60,w61,w62,w63 | Not Started |  |  |  | Yes
57 | w57 | Analysis and downstream work | Gerald closeout | Meeting with Gerald before analysis closeout | Krishna | w56 | w59,w63 | Not Started |  |  |  | Yes
58 | w58 | Analysis and downstream work | Stability study | Fully automated and stability study - Pawel and Noosheen | Pawel / Noosheen | w55 | w63 | Not Started |  |  |  | Yes
59 | w59 | Analysis and downstream work | Follow-up | Follow-up and review | Core Team | w57 | w63 | Not Started |  |  |  | Yes
60 | w60 | Analysis and downstream work | Adjudication work | Adjudication panel parallel work | Adjudication Panel | w25,w40,w56 | w63 | Not Started |  |  |  | Yes
61 | w61 | Analysis and downstream work | Afroditi analysis | Afroditi analysis | Afroditi | w55,w56 | w63 | Not Started |  |  |  | Yes
62 | w62 | Analysis and downstream work | Downstream errors | Downstream impact of errors research - Max and Joanna | Max / Joanna | w55,w56 | w63 | Not Started |  |  |  | Yes
63 | w63 | Analysis and downstream work | Final analysis | Final analysis | Analysis Team | w57,w58,w59,w60,w61,w62 |  | Not Started |  |  |  | Yes
Review Tasks Displayed in Dashboard
TaskID | Task | Owner | Status | Risk | DueDate | Dependency | Communication | Source | SourceDate | Display
task-phase1-05-001 | Identify additional eligible review | Core Team | Under Review | High | 2026-05-19 | Candidate pool | Shortlist review options. | Project tracking | 2026-05-14 | Yes
task-phase1-05-002 | Confirm team availability after candidate selection | Krishna / Review Team | Not Started | Medium | TBD | Review identification | Contact review team once candidate is selected. | Project tracking | 2026-05-14 | Yes
task-phase1-05-003 | [6 empty] | Assign one tool only after a review is selected. | Project tracking | 2026-05-14 | Yes
task-phase1-05-004 | [6 empty] | Start onboarding only after candidate and tool are confirmed. | Project tracking | 2026-05-14 | Yes
Recent Mail / Communication Log Displayed in Dashboard
CommunicationID | [6 empty] | Summary | LinkedTaskID | LinkedAction | SourceType | SourceLink | Display
comm-phase1-05-001 | [6 empty] | One additional eligible review still needs to be identified or confirmed for Phase 1. | task-phase1-05-001 | Identify additional eligible review | Project tracking |  | Yes
Critical Items Displayed in Dashboard
CriticalItem
Open Phase 1 review slot